## Infrastructure
S.No. | Problem | Priority Order | Resolution | Plan | Requirements | Estimations
1 | Eliminate single points of failure |  | Get separate machines for jboss, mongo, solr, batch, mysql as data is increassing. 2 machines for jboss, 1 Elastic load balancer, 2 machines for mongo, arbiter for mongo, 2 machines for solr, 1 machine for batch, 2 machines for mysql(master, slave)
2 | Increased reporting will slow down the application. |  | Get read replicas for mysql. We can create a db instance using snapshot just for read purpose. Reports will be generated using the read replicas.
3 | Data backup |  | MySql back is automatically handled by RDS. Mongo data back up can be stored in S3 and by setting rules.Periodically, data can be moved from S3 to Glacier. Solr data - Need to investigate.
4 | Regression testing before every deployment |  | To ensure existing functionality does not break and test new functioanlities more efficiently on data similar to production. 1. Automation Testing 2. Testing on staging by QA before release.
5 | Deployment process automation |  | By doing nightly builds, we can get to know integration issues well before time. We can also plugin automation test cases into this. Need to setup jenkins for this. With this, deployment will be just one click away.
6 | Cloudwatch for RDS, new relic monitoring for jboss
7 | VPC
8 | AMI

## Technology
S.No. | Technology | Pros & Cons | Priority | Plan | Requirements | Estimations
1 | Oauth
2 | Api driven

## Staging environment setup
| Tasks | Estimates
1 | POC on dynamic Java configuration as 1st safety layer | 2
2 | Prepare classes for dynamic Java config change | 4
3 | Test dynamic config change thoroughly | 3
4 | Analyse how to add 2nd safety layer - masking data is 1 option | 2
5 | Identify what data to mask | 2
6 | Prepare appropriate Roles/Users on the AWS platform for Staging | 2
7 | Preparing script to mask PROD SQL data | 2
8 | Setup RDS instance with PROD SQL data | 1
9 | Prepare script to mask MongoDB data (if required) | 4
10 | Setup EC2 instance with MongoDB data | 1
11 | Prepare script to mask Solr data (if required) | 2
12 | Setup Solr data on the EC2 instance with MongoDB | 1
13 | Setup EC2 instance with JBoss server and batches | 2
14 | Prepare AMI for instances | 2
28
2nd safety layer options:
Block at sendgrid level
Physically remove email sending/social media posting classes
Mask email addresses
Post to Social media - but use dummy accounts

## Performance changes
| Tasks | Estimates
1 | Change datatype of Agent_ID to long in DB | 1
2 | Change datatype of Agent_ID to long in DB - test extensively | 2
3 | Analyse connection pooling | 2
4 | Analyse most called/slowest web transactions - optimise Java code | 2